## Sheet1
ID | User Story Description |  |  | Acceptance criteria | Story Points
| Well-formed | Atomic | Conceptually sound
US001 | As an adventure seeker | I want to "sign up" in the system | So that I can login | Sign Up page contains a form with the following fields. 1. Create a new User sign up page with details- username, password, name, preferences, skill level, attitude. 2. Save the User details in the Database using encryption. | 5 points
US002 | As an adventure seeker | I want to "sign in" with my credential | So that I can get access to the primary features | Sign In page should conatin following: 1. Create an login page for existing user, with username and password tabs and a submit button. 2. Authenticate the User on login, based on the encrypted username and password. | 3
US003 | As an adventure seeker | I want to edit my profile | So that I can modify the profile information | Profile page should consists of following: 1. Users should be able to edit their personal information. 2. Users should add and remove information | 3
US004 | As an adventure seeker | I want to delete my profile | So that I can remove my details from the system | Delete profile page should contain the following: 1. Provide a delete profile option in the User's profile page, with options to delete just the profile and persist the user details or delete all the details of the user from the records. 2. Once the User deletes the profile, delete the details of the User from the database as per the option selected. | 3
US005 | As an adventure seeker | I want upload photos in my Profile | So that other users can view them | Uploading photos page should contain the following: 1. Upload Photos from Computer 2. Drop photos from computer 3. Submit button 4. Photo should be saved in database againts the user profile | 5
US006 | As an adventure seeker | I want to delete photos in my Profile | So that I can remove unwanted photos | Deleting photos page should contain the following: 1. Option to select 'delete photo' 2. Ask for confirmation to delete 3. All information should be deleted from the database | 4
US007 | As an adventure seeker | I want to connect my Profile to Social Media | So that I can sink my updates to my social media profile at the same time | Connect social media page should contain the following: 1. Create a link for the User to be able to connect to Instagram, Facebook, Snapchat, and Tinder. 2. Third party application should verify the identity. | 6
US008 | As an adventure seeker | I want to modify my adventure interests in the profile | So that I can keep my interests updated | Aadvebture interests should contains the following: 1. Allow to add/remove/update adventure interest, skills, preference 2. Save button 3. All data should be saved to database | 3
US008 | As an adventure seeker | I want to find the right adventure partner | So that I can initiate conversation | Finding partner should contains the following: 1. Create a matching algorithm to match User's preferences and find an adventure partner based on difference factors. 2. Display the matched partners based on the preferences. | 8
US0010 | As an adventure seeker | I want to block an unwanted profile | So that I can avoid unwanted users | Blocking feature should contains the following: 1. Provide a button (Block this User) 2. User's profile should not appear on Blocked users | 3
US0011 | As an adventure seeker | I want to get the notification for matching profile is found | So that I can show my interest to right individual | Should contains the following: 1. System shall analyze the users preferences and detect matches 2. System shall send 'push' notification or 'email' notification | 4
US0012 | As an adventure seeker | I want to send message to a co-adventurer | So that I can send message and chat with other users | Communication module should contains the following: 1. Messaging/Chat option | 5
US0013 | As an adventure seeker | I want to make calls with co-adventurer | So that I can communicate using audio or video call | Communication module should contains the following: 1. Call option (audio and video) | 7
US0014 | As an adventure seeker | I want to view view my in-app messaging history | So that I can check the messages | View message should contain the following: 1. View messages | 3
US0015 | As an adventure seeker | I want to delete my in-app messaging history | So that I can remove unwanted messages | Delete message should contain the following: 1. Delete the messages 2. System should remove deleted messages from database | 3
US0016 | As an admin | I want to check the adventures list | So that I can check the adventurers who signed up | System shall consist of a special permission/option/features for admin to access the list | 4
US0017 | As an admin | I want to see the details of adventure seekers | So that I can monitor the adventurers | System shall consist of a special permission/option/features for admin to access the details of adventure seeker | 5
US0018 | As an admin | I want to terminate the adventurers seekers profile | So that I can remove unwanted/violated users | System shall consist of a special permission/option/features for admin to remove registered adventure seeker | 3
US0019 | As an admin | I want to delete contents from blog of adventure seeker | So that I can remove unwated contents from user blog | System shall allow admin to remove any features of adventurers | 3